Doubow

Engineering Build Plan

Version 1.0  ·  May 2026  ·  16 Weeks to MVP

Tech Stack

| Layer | Technology | Rationale |
| --- | --- | --- |
| Frontend | Next.js 14 + TypeScript | SSR/SSG, file-based routing, strong ecosystem |
| UI Components | shadcn/ui + Tailwind CSS | Accessible, unstyled primitives; rapid iteration |
| Backend API | FastAPI (Python 3.12) | Async-native, Pydantic, auto-generated OpenAPI docs |
| Task Queue | Celery + Redis | Background workers for scraping, AI, PDF parsing |
| Database | PostgreSQL 16 + pgvector | Relational state machine + vector similarity search |
| AI / Agents | LangChain (modular) | Plug-and-play agent/tool composition |
| LLM Provider | Anthropic Claude + OpenAI fallback | Quality + redundancy |
| Object Storage | AWS S3 (or compatible) | Résumé files, raw HTML, generated PDFs |
| Auth | NextAuth.js + JWT | Session management, OAuth (Google, LinkedIn) |
| Payments | Stripe + Customer Portal | Subscriptions, webhooks |
| Observability | Prometheus + Grafana + Sentry | Metrics, tracing, error tracking |
| CI/CD | GitHub Actions → Docker → ECS | Reproducible builds, zero-downtime deploys |

Application State Machine

DISCOVERED → SCORING → DRAFTING → PENDING_APPROVAL → APPROVED → SUBMITTED (any state) → FAILED → RETRY → (resumes from failed point)

Enforcement rule: The /applications/{id}/submit endpoint checks status = APPROVED in the database. If not, it returns HTTP 403. This check is in the API handler — it cannot be bypassed by a direct API call.

Engineering Phases

| Phase 1: Foundation & Plumbing · Weeks 1–3 · 2 BE + 1 DevOps |  |
| --- | --- |
| ✓ | Postgres schema: users, profiles, jobs, applications, outreach_drafts, llm_logs, check_ins, milestones |
| ✓ | Application state machine with Alembic migrations |
| ✓ | FastAPI project structure with Pydantic v2 schemas |
| ✓ | Celery + Redis queues (scrape, score, draft, notify) with dead-letter queue |
| ✓ | JWT authentication + Google / LinkedIn OAuth |
| ✓ | Résumé upload worker: PDF/Docx parse → structured JSON → embedding via text-embedding-3-small |
| ✓ | Idempotency key middleware (deduplicates within 24h window) |
| ✓ | S3 object storage for raw résumé files |
| 🚦 Gate: State machine enforces transitions. POST /applications/{id}/submit returns 403 unless status = APPROVED in DB. |  |

| Phase 2: RAG & Matching Core · Weeks 4–6 · 2 BE + 1 ML |  |
| --- | --- |
| ✓ | Job scraper workers (pluggable strategy per source, rate-limited, raw HTML stored in S3) |
| ✓ | Job embedding pipeline: text-embedding-3-small → pgvector (HNSW index) |
| ✓ | Fit Scorer agent: structured JSON output { score, match_pct, rationale, gap_skills, strength_skills } |
| ✓ | Pydantic validation on all agent outputs — invalid → FAILED state + alert |
| ✓ | Job catalog REST API with filter/sort/pagination |
| ✓ | Match feed endpoint: cosine similarity ranking against user résumé embedding |
| ✓ | Deduplication: hash(source_url) as unique key per job |
| 🚦 Gate: Scorer reliably produces structured JSON. Invalid outputs are caught and flagged before reaching the DB. |  |

| Phase 3: Agentic Layer · Weeks 7–9 · 2 BE + 1 ML |  |
| --- | --- |
| ✓ | Drafter Agent: email + LinkedIn message drafts stored as status=DRAFT in outreach_drafts |
| ✓ | Interview Prep Agent: RAG-grounded with job description + résumé context |
| ✓ | Sender Agent: triggered ONLY when applications.status = APPROVED — dispatches email or LinkedIn |
| ✓ | LLM interaction logging: agent_name, prompt_hash, raw_output, latency_ms, user_edit, feedback_score |
| ✓ | Retry / FAILED state handling with exponential backoff (max 3 retries) |
| ✓ | Unified Assistant (Career Copilot): LangChain agent with 6 structured tools + WebSocket streaming |
| ✓ | Conversation history stored per session (last 20 turns in context) |
| 🚦 Gate: Full DISCOVERED → PENDING_APPROVAL flow works end-to-end. Sender cannot fire without APPROVED in DB. |  |

| Phase 4: UI & Approval Dashboard · Weeks 10–13 · 2 FE + 1 BE |  |
| --- | --- |
| ✓ | P0 — MVP Critical: Onboarding wizard, Career Profile, Dashboard, Approval Dashboard, Job Discovery, Job Tracker, Career Copilot |
| ✓ | P1 — Launch Complete: Career Planner, Career Pathfinder, Career Success, ATS Optimizer, Settings/Stripe |
| ✓ | P2 — Post-Launch: CV Builder, Cover Letter, Career Health, LinkedIn Analysis, Salary Benchmark, Sponsorship Hub, Discussion Board |
| ✓ | Design system: dark navy sidebar (#0F1117), white content area, blue accent (#4F8EF7), shadcn/ui |
| ✓ | TanStack Query for server state, Zustand for client state |
| ✓ | Approval Dashboard: inline edit, approve (→ APPROVED), reject — real-time status via WebSocket |
| 🚦 Gate: All P0 pages shipped and approved by QA. Approval flow tested end-to-end with HITL enforcement verified. |  |

| Phase 5: Production Hardening · Weeks 14–16 · Full team |  |
| --- | --- |
| ✓ | Prometheus metrics: request latency, worker queue depth, FAILED rate, LLM latency, scraper success |
| ✓ | Grafana dashboards: pipeline health, agent performance, user funnel |
| ✓ | Rate limiting: scraper (per domain), LLM (token budget per tier), API (100 req/min per user) |
| ✓ | GDPR: /users/me/delete endpoint, audit log table, data retention policy, cookie consent |
| ✓ | Drift detection: monthly cron checks edit rate per agent — alert if > 40% |
| ✓ | k6 load tests: 500 concurrent users, p95 < 500ms |
| ✓ | GitHub Actions CI/CD: lint → test → build → push → deploy → smoke test → promote to prod |

Dependency Map

External Dependencies — Acquire in Week 1

- Anthropic API key (primary LLM)

- OpenAI API key (embeddings + fallback)

- LinkedIn API access (allow 4–6 week approval time — critical path)

- AWS S3 bucket + IAM roles

- Stripe account + webhook endpoints

- Email sending service (SES or Resend)

Risk Register

| Risk | Severity | Mitigation |
| --- | --- | --- |
| HITL enforcement bypassed via direct API | Critical | 403 in Sender endpoint unless DB status = APPROVED |
| Scraper blocked / CAPTCHA / DOM changes | Critical | Decouple scraper; store raw HTML separately; scraper failures don't block downstream |
| LinkedIn API rejected or revoked | Critical | Build Sender as provider-agnostic; email-first fallback always available |
| LLM output schema drift | High | Pydantic validation on all agent outputs; invalid → FAILED state + alert |
| Résumé parse quality degrades scoring | High | User can edit parsed fields; quality check on extraction; fallback manual entry |
| Celery task duplication on restart | High | Idempotency key on every sensitive task (Phase 1 deliverable) |
| UI scope underestimated | Medium | Launch with P0 pages only; P1/P2 post-launch using phased rollout |
| GDPR / PII compliance | Medium | Schema-level design in Phase 1; not retrofitted later |
| Scoring drift over time | Low | Monthly drift detection cron; compare edit rate vs model recommendations |

Team & Responsibilities

| Role | Count | Responsibilities |
| --- | --- | --- |
| Backend Engineer | 2 | FastAPI, state machine, DB schema, workers, agent integration |
| ML / AI Engineer | 1 | Agent design, RAG pipeline, embedding quality, prompt engineering |
| Frontend Engineer | 2 | Next.js UI, component library, approval dashboard, chat interface |
| DevOps Engineer | 1 | Infrastructure, CI/CD, observability, security hardening |
| Product Manager | 1 | Requirements, prioritization, stakeholder communication, KPI tracking |
| Designer | 1 | Design system, component specs, user testing, accessibility |

Definition of Done (MVP)

- User can register, upload résumé, and complete Career Profile

- Job Discovery shows personalized match feed with fit scores

- User can track applications through the full pipeline

- AI generates outreach drafts and surfaces them in the Approval Dashboard

- No draft can be sent without explicit approval (verified by penetration test)

- Career Copilot answers career questions with context from user's résumé

- ATS Optimizer returns keyword match and improvement suggestions

- Stripe subscription flow works end-to-end (Standard / Pro / Ultimate)

- All P0 pages pass WCAG 2.1 AA audit

- p95 API response < 300ms under 500 concurrent users

- GDPR deletion endpoint tested and verified